## Doc.Info
CM Audit Checklist
Telstra Non Discretionary
Telstra
Document Version History
Ver. No. | Ver. Date | Prepared By | Reviewed By | Approved By | Description
1 | 2016-03-22 | Nishant Mahajan | Niteen Acharya | Natesh Palahalli | CM Checklist for March-2016
As we have completely migrated all the documents from VSS to StarTeam henceforth CM Audit report will be generated from StarTeam and maintained in the same location (BASI-Telstra CC\Telstra ND\2.5_Config_Mgmt)
Note on A2: Replace with the project name here
Note on A3: Replace with the customer name here
Note on A7: Typein Version number. For ex: 1.1
Note on B7: Type-in " dd-MM-yy" format. Ex: "01-Jan-07"

## CM Audit
Configuration Management Audit Checklist
Date of Audit: 22-March-2016
Auditee Name / Role: Nishant Mahajan, CM Lead
Auditor Name / Role: Niteen Acharya, SQA
S# | Check Description | Status | Remarks [Mandatory if Status is No / NA]
1 | Are all non-conformances identified in the previous audit closed? | Yes | No issues identified till date.
2 | Are all configuration items identified in the CM plan in sync with those maintained in the CM tool? | Yes
3 | Has the CM lead performed the backup verification and backup restoration checks with the SMT as per the frequency stated in the CM plan? | NA | Ownership of code and server back up lies with client and third party.
4 | Does the folder structure match whatever has been stated in the CM plan? | Yes
5 | Does the CM tool access rights provided to the team members match whatever has been stated in the CM plan? | Yes | Implemented for all team members
6 | Are CI status reports generated as and when required? | Yes
Perform random sample checks for the following and mention the details of the chosen sample in the Remarks column of this report
1 | Have check-in comments been provided in the CM tool for every check-in? | Yes
2 | Has the CI been maintained regularly [frequent, almost daily check-ins] in the CM tool? | Yes
3 | Has any file been checked out for >= 2 working days? | No
4 | Have deliverables been named as per the conventions mentioned in the CM plan? | NA | CM is only limited to maintain the Application related process documents
5 | Have deliverables been labeled as per the data classification guidelines (including customer-specific labeling) mentioned in the CM plan? | NA | CM is only limited to maintain the Application related process documents
6 | Does the latest version in the CM tool and the revision history match? | Yes
7 | Does the version history follow the version numbering scheme stated in the CM plan? | Yes
8 | Are branches created and merged as per the CM plan? | NA | CM is only limited to maintain the Application related process documents and project CIs
9 | Are assets provided by supplier / customer managed as stated in the CM plan? | Yes | It is handled at Account level
10 | Are hard copy assets managed as stated in the CM plan? | NA
Change Request Checks
1 | Are change requests logged and tracked as mentioned in the CM plan? | Yes | CM is only limited to maintain the Application related process documents and Application Cis
2 | Is the status of a change request correctly maintained in the change request log? | Yes
3 | Are change requests analyzed for impact on scope, schedule, effort, technology and the impact analysis results recorded as mentioned in the CM plan? | Yes
4 | Are CCB approval records maintained? | Yes
5 | Is the RTM updated for all approved change requests? | NA
Baseline Verification Checks [Select an approved change request at random and verify the following]
1 | Has the baseline criteria been met? | Yes
2 | Are the configuration items associated with the baseline same as the artifacts being impacted by the change? | Yes
3 | Has the baseline been named as per the conventions mentioned in the CM plan? | Yes
4 | Have phase-wise baselines been created? | NA
5 | Are baselined versions safeguarded from accidental check-out / edit? | Yes
Release Verification Checks [Select an approved change request, that is awaiting a release to the customer, at random and verify the following]
1 | Have release-wise baselines been created? | NA | Not Applicable for PS&M This activity is done by separate development team and approval done by application manager.
Are the following documents available during the audit?
2 | Requirement Specifications | NA
3 | Design Documents | NA
4 | Unit Test Plan | NA
5 | System Test Plan | NA
6 | Tested / Approved Code | NA
7 | Unit Test Cases and Test Results | NA
8 | System Test Cases and Test Results | NA
9 | Requirements Traceability Matrix [Updated for all phases complete till now] | NA
10 | Change Request Log | NA
11 | User Manual | NA
12 | Were all performance parameters verified during testing? | NA
13 | Have all the defects captured during testing been fixed? | NA
14 | Is there any plan to close the defects that could not be fixed? | NA
15 | Is the release note approved by the project manager? | NA