## Doc Ino
SQA Audit Checklist and Report - Apps Mgmt (ITSM) Project |  |  |  |  | Largely Implemented | • Direct artifacts present & appropriate • Supported by indirect artifact &/or affirmation • No weakness noted
Project Name |  |  | TPNI |  | Partially Implemented | • Direct artifacts absent or judged inadequate • Artifacts or affirmations indicate some aspects of the practice are Implemented • One or more weaknesses noted
Customer Name |  |  | Telstra |  | Not Implemented | • Any situation not covered by above
Reporting Period/Month |  |  | 2016-08-01 |  | Not yet Implemented | Phase / Stage not reached for this check
Project Manager Name |  |  | Natesh Palahalli |  | Not Applicable | This check is not applicable as per project scope
Document Version History
Ver. No. | Ver. Date | Prepared By | Reviewed By | Approved By | Description
1 | 2016-08-22 | Niteen Acharya | Nishant Mahajan |  | SQA Checklist for August-2016
Note on A2: As in PPMC
Note on F4: Phase/Stage yet to reach
Note on A9: Type in Version number. For ex: 1.1

## Planning and Monitoring
SQA Audit Checklist For ITSM Projects
Sl No. | Questions | Status | Link to Evidence | Description of the observation
Project Planning
1 | Is SDMP reviewed and approved as per the project scope based on the SoW / SLA? | Largely Implemented |  | Reviewed and approved by Quality team.
2 | Is Service Delivery and Monitoring plan (SDMP) and other plans reviewed by Quality team? | Largely Implemented |  | Reviewed and approved by Quality team.
3 | Is tailoring and waiver plan reviewed and approved by the Quality Team? | Not Applicable
4 | Is SDMP, Team development plan and other related plans reviewed and approved Program manager? | This phase not yet reached
5 | Is security plan reviewed by the ISMS team? | Largely Implemented |  | As per HP Communiction.
6 | Is security plan approved by the ISMS team ( In case of rating is " HIGH") ? | Largely Implemented
8 | Is Business Impact analysis document reviewed by BCMS team? | Largely Implemented
9 | Is Risk assessment(RA) document reviewed by BCMS team? | Largely Implemented
10 | Is Business Impact analysis(BIA) and RA document approved by the Delivery Head? | Largely Implemented
11 | Is Business recovery plan ( BRP) reviewed and approved by Program Manager? | Largely Implemented
12 | Are all the plans baselined in CM tool? | Largely Implemented
Training and Awareness
1 | Have the team members completed the mandatory (SBC) trainings, including ISMS and BCMS ? | Largely Implemented |  | SBC and ISMS has been done and DD need to schedule BCMS training
2 | Has the project team completed the EDGE overview training? | Largely Implemented
3 | Are all team members trained on ITIL? | Largely Implemented |  | The basic certification has been completed by all team members and for advance certification, Natesh has to schedule in next quarter via grow@Hp.
4 | Is SQA / CM and project relevant role based trainings completed? | Largely Implemented
Project Monitoring
1 | Is there a scope change for the project? if "YES", is the SoW revised and approval from the Customer taken on the same? | Largely Implemented |  | The scope of support has been canged and got the sow approved for the same
2 | As per the current scope are the project plans are revisited and updated? | Largely Implemented |  | Yes
3 | Is Team development plan reviewed at regular intervals and up to date ? - Skill threshold values and skill assessor have been identified - Skill Required and Available have been updated based on the training provided | Largely Implemented |  | Yes
4 | Approval from the Pgm Mgr available for the updated project plans? | This phase not yet reached |  | SDMP aproved and reviewed by QA
5 | Are project identified issues logged and tracked in PPMC tool? | Largely Implemented
6 | Are the project identified risks logged and tracked in PPMC? | Largely Implemented
7 | Is the effort expended by the team tracked ? | Largely Implemented
8 | Is the staffing profile updated as per current project? | Largely Implemented |  | Yes
9 | Is LoS report submitted in PPMC month on month basis with in the time frame? | Largely Implemented |  | Yes
10 | Are team meetings being held on a weekly basis, MoMs prepared and action items tracked to closure ? | Largely Implemented |  | forthnightly team meetings are held.
11 | Are the Customer reviews are conducted and MoM /action items are tracked per the frequency? | Largely Implemented |  | Monthly Governance meetings are coducted with customer
12 | Are the findings of the previous External / Internal /IQHC/PRB/ SQA Audit closed ? | This phase not yet reached
13 | Are the budgeted and actual cost and effort are updated and tracked in PPMC | Largely Implemented |  | Yes
14 | Whether the tasks in PPMC are defined in sufficient granularity to enable effective analysis and control? | Largely Implemented
15 | Are the deviations in estimated and actual efforts analyzed and action taken to manage the variance? | Not Applicable
16 | Is effort analysis done by the PM on regular basis? | Largely Implemented
17 | Are PMRs being conducted each month, MoMs prepared and action items being tracked to closure? | Largely Implemented
18 | Project monthly metrics submitted in the metrics portal? | Largely Implemented |  | PM to submit monthly metrics report and I have to check with Patil
19 | Is the project retrospective being conducted once in a year? | Not Applicable
20 | Are best practices / Service improvement plans (SIP) and project data being submitted after every project retro ? | Not Applicable
Customer relationship management
1 | Is Accounts Satisfaction Survey conducted for the project? | Largely Implemented |  | Monthly Governance meetings are coducted with customer
2 | Is Root cause analysis done on account satisfaction report & Improvement actions shared with stake holders? ( If applicable) | Largely Implemented |  | Progress reported through Meeting reports
3 | Are there adequate mechanisms to handle various kinds of Account /Region / Customer complaints and feedbacks / appreciation ? | Largely Implemented |  | Yes
4 | Are there action plans in place to deal with Account /Region / Customer feedback/complaints? | Largely Implemented |  | Yes
5 | Is there a review process to assess whether the action plan is successful? | Largely Implemented |  | PIR Conducted- Customer and HP
Project Closure Process
| Is project closed in PPMC? | Largely Implemented
| Is the project retro been conducted? | This phase not yet reached |  | This is a Support Project, Retro is conducted six Months to analyze the Project.
| Is Knowledge Contribution to Organization through SAVE TO SHARE process http://teams10.sharepoint.hp.com/teams/ProjectClosure/default.aspx | Not Applicable
| All assets/artifacts that are customer assets/artifacts formally returned to the customer | Largely Implemented
Note on F4: If Status is "Yes", provide a link to evidence, if Status is "No", provide a brief explanation.
Note on C21: If there is change in SQA the new SQA / CM has to undergo the training.

## SQA Audit Report
Project Name |  | TPNI | All PMR / SQA / IQHC /PRB findings to be looked and logged in PPMC and tracked to closure.
Project Manager
Project SQA
Report Prepared On |  | 2016-08-22
S.No | Check List | Comment | Findings / Issues | Planned Closure Date | Actual Closure Date | Status
1 | Have the team members completed the mandatory (SBC) trainings, including ISMS and BCMS ? |  |  |  |  | Closed | No
2 | Are all team members trained on ITIL? | All of the members of the team are ITIL certified. Web based trainings are completed by all team members. 2012 Nishant\Pawan completed earlier. 03/Apr/2013 Deepika got Certified In March Month Jan-Feb-2014 Gopi\Niteen\Manju completed in jan and feb month. Mar-2014 Hitarth completed in March. April-2014 Srinithya completed ITIL June-2014 Haripriya\Rukkaya May-2015 3 New joinees in the team Rest all memebrs of the team are now ITIL certified. July-2015 one more new joinee in the team Oct-2015 one more new joinee in the team Rajeev has already completed ITIL Jan-2016 one resource left Mar-2016 2 freshers have joined the team. Sindu has already completed ITIL exam Sunadar has not done ITIL 2 resources have released from team for onsite assignment. Hitarth and Srinithya June - 2016 Gopi has joined support team July - 2016 Deepankar Rai has joined team August - 2016 One more resource released for Everest Project. | No Issues, everyone passed the exam. |  |  | Closed
3 | Are cross training done on equal intervals inside the team? | Trainings for GDD team members to be organised between month of Dec to feb, training plan yet to be finalised |  |  |  | Closed
4 | Team has to go through ITIL in Grow@hp | 99% Completed |  |  |  | Closed

## Project Initiation and Kickoff
SQA Audit Checklist For ITSM Projects
Sl No. | Questions | Status | Link to Evidence | Description of the observation
Project Initiation
1 | Is SoW / SLA exists between BAS India and HP- Accounts team / First line Customer? | Largely Implemented
2 | Is SoW / SLA document signed off by the HP-Accounts team / First line Customer? | Largely Implemented
3 | Is transition exit criteria met and sign off completed by the PM? | Largely Implemented |  | Yes
4 | Is project created in PPMC? | Largely Implemented |  | Yes
5 | Is staffing profile created in PPMC? | Largely Implemented |  | Yes
6 | Is work plan created in PPMC for the project team members? | Largely Implemented |  | Yes
7 | Is project status active in PPMC? | Largely Implemented |  | Yes
8 | Is project planned budget entered in PPMC? | Not Applicable |  | As the budget is shared across all ND apps, could not get exactly how much is the $ value
9 | Are the required roles identified for the project? (Pgm mgr, PM, SQA, CM Lead, ISMS SPOC, QA SPOC, KM Lead) | Largely Implemented
10 | Is project kick off meeting conducted with relevant stakeholders? (Industry, Service Line,PRB, Biz Ops, Q Ops, HR, L&D, PM, PGM, SQA, CM Lead, ISMS and BCMS Representatives) | Largely Implemented
11 | Is signoff available from the relevant stakeholders on their required support for the project requirements mentioned in the project Kickoff? | Largely Implemented
12 | Is project Kick off MoM available and action items are tracked? | Not Applicable
13 | Is CM tool ( StarTeam ) configured for the project team members? | Largely Implemented
14 | Is call management tool configured and set up for the project? | Largely Implemented
Note on C5: EDGE BAS India SoW Template to be used.
Note on E5: StarTeam Path

## Service Management
SQA Audit Checklist For ITSM Projects
Sl No. | Questions | Status | Link to Evidence | Description of the observation
Incident Management
1 | Is an incident database maintained for logging and tracking all reported incidents ? | Largely Implemented | iTam
2 | Are incidents classified based on incident or service request, and prioritized based on urgency and impact and assigned to the right group? | Largely Implemented | iTam
3 | Is there a process for assigning, monitoring, tracking incidents and is followed for the all the incidents? | Largely Implemented | iTam-RRT will do this
4 | Is there a procedure for the closure of incidents? | Largely Implemented | Yes in iTam
5 | Does incident management provide the user with progress updates on the status of the incident ? | Largely Implemented | Yes
6 | Is the quality of the update comments verified by means of sampling ? | Largely Implemented | iTam
7 | Is the reason for putting calls in "Pending" status communicated, and is the status of pending calls tracked ? | Largely Implemented | iTam
8 | If the resolution of an Incident will not be on time or satisfactory then, is there a procedure defined for "Hierarchical Escalation" (senior management)? | Largely Implemented | iTam
9 | In case of security incidents, are these raised with the right group ? | Largely Implemented | Yes
10 | Does the incident owner do a shift handover when he transfers the ownership ? | Largely Implemented | Yes
11 | Is the resolution/ work around validated with the user before closing the ticket ? Is there procedure for deemed acceptance while closing a ticket ? | Largely Implemented | iTam
12 | Is there an incident manager responsible for managing and escalating incidents? Is the management Communicated about Escalated Incident ? | Largely Implemented | Yes
13 | Is there a trend analysis done on the incidents and relevant report are generated and analyzed? | Largely Implemented | Yes
14 | Does incident management match incidents against the KEDB ? | Largely Implemented | Yes
15 | Does incident management exchange information and have access to information to other Service Management process areas like with Problem Management concerning related problems and / or KEDB? Or CM for CMDB | Largely Implemented | Yes
Problem Management
1 | Is there a problem record maintained with all the details and solution? | Largely Implemented
2 | Is there a procedure by which potential problems are classified, in terms of category, urgency, priority and impact and assigned for investigation? | Largely Implemented
3 | Are work around updated in the KEDB and communicated to the incident management team ? | Largely Implemented
4 | Are the resolutions and work around provided based on the root cause analysis and RCA records are maintained ? ? | Largely Implemented
5 | Is an RFC initiated to correct the known error and tracked till closure ? | Largely Implemented | PKE will be created to track the know error
6 | Are triggers for proactive problem identification defined ? | Largely Implemented
7 | Is there a known error database (KEDB) maintained? | Largely Implemented
8 | Does PM exchange information and interact with other process areas like transferring knowledge to Incident Management on Known Errors | Largely Implemented
Change Management
1 | Are all Requests for Changes recorded and classified ? | Largely Implemented
2 | Is there a procedure for approving, verifying and scheduling changes? | Largely Implemented
3 | Is the emergency change process documented and adhered to? | Largely Implemented
4 | Are change records maintained to reflect the progress of changes? | Largely Implemented
5 | Are changes planned and prioritized? | Largely Implemented
6 | Is Impact Analysis been done for the changes to be undertaken ? | Largely Implemented
7 | Is the RFC tracked till closure ? | Not Applicable
8 | Does CM exchange information with other Management Process areas ( Ex- Release Management concerning change implementation?)? | Largely Implemented
9 | Are Post Implementation Reviews conducted after changes are implemented ? | Largely Implemented
Release Management
1 | Are at least some release management activities established within the project? a) Procedures for the release b) Procedure for Build & Test c) Mode of Application Deployment / Move to Production | Largely Implemented
2 | Has release planning been done ? | Largely Implemented
3 | Are there release naming and numbering conventions being followed ? | Largely Implemented
4 | Have roles and responsibilities for various release management activities been assigned between operational groups and development teams? | Largely Implemented
5 | Is the release schedule shared and reviewed with all stakeholders ? | Largely Implemented
6 | Are release notes prepared ? | Largely Implemented
7 | Is a release checklist available ? | Largely Implemented
8 | Are test plans, acceptance criteria and test results produced for each Release? | Largely Implemented
9 | Is an audit being done before the release ? | Largely Implemented
10 | Is there a back out plan available for each release ? | Largely Implemented
11 | Are metrics related to number of major and minor releases being reported ? | Not Applicable
Configuration Management
1 | . Are the configuration management activities established within the project? a) Uniquely Identifying the Configuration Items (CI) b) Recording the CI and their attributes (CMDB) and relationship among the Cis | Largely Implemented
2 | Are Configuration Items maintained in a version controlled environment with access restricted to authorized users ? | Largely Implemented
3 | Whether Customer supplied assets / CI are maintained? | Largely Implemented
4 | Are the update access to CIs are controlled and history and status maintained for CIs and procedure for informing the CI changes | Largely Implemented
5 | Have naming conventions been agreed upon for configuration items ? | Largely Implemented
6 | Is a configuration management audit conducted as specified and action items tracked to closure ? | Largely Implemented
7 | Does Configuration Management interface with other management services? (Providing information to the Change Management in assessing the impact of a requested Change) | Largely Implemented
Service Level Management
1 | Has the SLA been agreed upon with the Account / First line Customer and signed off? | Largely Implemented
2 | Do SLAs have clearly identified key targets for service hours, availability, reliability, support, response times and change handling? | Largely Implemented
3 | Are standard service reports produced regularly? | Largely Implemented
4 | Are there any specific customer security requirements ? If yes , whether this is documented in the SLA ? Whether SLA captures the reduced service operating level in the event of a disaster ? | Largely Implemented
5 | Are there any specific customer security requirements ? If yes , whether this is documented in the SoW / SLA ? Whether SLA captures the reduced service operating level in the event of a disaster ? | Largely Implemented
6 | Are there OLA s'/UCs with internal organizations/Vendors to support the customer SLA? | Largely Implemented
7 | Are there appropriate mechanisms in place to measure and monitor all items in SLA? | Largely Implemented
8 | Are issues with SLA adherence being reviewed as part of senior management and customer reviews ? | Largely Implemented
9 | Are there appropriate mechanisms in place to measure and monitor all items in SLA? | Largely Implemented
10 | Is there any Service Improvement identified , planned and tracked to closure? ( SIP ) | Largely Implemented
11 | Are there any actions taken for the SLA breaches(if any) and customer updated on breaches and action items ? | Largely Implemented
12 | Are all the project team members aware of the service management objectives which is documented in the Service Level Agreement ? | Largely Implemented
13 | Does the SLM exchange information and interface with other Management Areas ( Like SLAs ?OLAs are under Change management Control ) ? | Largely Implemented
Capacity Management
1 | 1. Are at least some capacity management activities established within the Project/ organization? a) monitoring of usage and performance b) capacity planning c) sizing of service elements | Not Applicable
2 | Has the scope of capacity management been determined? | Not Applicable
3 | Is there a capacity plan available? | Not Applicable
4 | Does the Project/ organization have a process to ensure that there is sufficient capacity to support planned services? | Not Applicable
5 | Are there mechanisms for analyzing resources/system usage and for reporting on performance? | Not Applicable
6 | Do procedures exists to forecast their resource requirements based on the new workloads and to ensure that adequate capacity is provided to meet the current and future workloads/business needs | Not Applicable
7 | Does the capacity management process exchange information with other Management Process areas to the business continuity process? | Not Applicable
Availability Management
1 | Has the scope of availability management been identified and established? | Largely Implemented
2 | Have the availability requirements of the business been identified and documented? | Largely Implemented
3 | Do you have defined targets for the availability that are documented and agreed in SLAs? | Largely Implemented
4 | Are there mechanisms in place for identifying service (un)availability and IT component failure? | Largely Implemented
5 | Do you have procedures for monitoring, analyzing, and forecasting service availability? | Largely Implemented
6 | Do you have procedures for managing data backup and recovery? | Largely Implemented
7 | Do you investigate the underlying reasons for unplanned non-availability and corrective actions are undertaken? | Largely Implemented
8 | Are standard reports on IT service availability produced and Plan reviewed on a regular basis? | Largely Implemented
9 | Does Availability Management exchange information with other Management areas ( Ex- Problem Management concerning IT service downtime? With Capacity management to take in to account of availability requirements and trends in system usage?) | Largely Implemented
IT Service Continuity Management
1 | Is the Business Continuity Plan (linking the Business Recovery Plan of the project with the Center level BCP) published and communicated to the Project Team? | Largely Implemented
2 | Has the team identified CSH in case the project is Company critical or Essential for Business ? Are the CSH trained on additional technologies to take over in case of any Business disruption? | Largely Implemented
3 | Are the ERT member identified in the project area and trained on DO's and Don'ts in case of emergency? | Largely Implemented
4 | Are contact numbers of team members available ? | Largely Implemented
5 | Is this regularly reviewed and procedures tested and updated ? | Largely Implemented
6 | Are all team members aware of continuity plans and recovery measures ? | Largely Implemented
7 | Is there a check-list covering the specific actions required during all stages of recovery of the system? | Not Applicable
Operations Management
1 | Is there a standard technical / operations guide available for the activities to be carried out? | Largely Implemented |  | Yes - Operational manual should be available in start team
2 | Is a Operational checklist available ? Is this reviewed and updated after outages ? | Largely Implemented |  | Yes - should be available in Star team
3 | Are the operations management reports prepared regularly with clear achievement figures against operating level objectives (e.g. unplanned downtime) ? | Largely Implemented |  | Yes, Monthkly reports will be sent to Telstra through OMCPR- Joel wil do this
4 | Are metrics reported for operations management ? | Largely Implemented |  | same as above
Security Management
1 | Is there a regular updation of Anti-Virus software patches ? | Largely Implemented
2 | Does the Security Plan address the Customer Security Requirements ( wherever applicable)? | Largely Implemented
3 | Are all team members aware of hp's security policy, and if applicable, the customer's security policies ? | Largely Implemented
4 | Is the security plan revisited and current? | Largely Implemented
5 | Is there an exit procedure/checklist defined and followed for engineers moving out of the team ? | Largely Implemented
Note on F4: If Status is "Yes", provide a link to evidence, if Status is "No", provide a brief explanation.
Note on C6: Although incidents may be reported via email or telephone, they need to be recorded in the Incident Mgmt. Database.
Note on C16: An agreed duration within which customer needs to respond to the resolution provided, failing which the resolution is deemed to be accepted.
Note on C27: Could be through analysis of incident data, through RCA done on high impact incidents or for unplanned failures
Note on C110: Removal of access to project assets etc.

## Legal Statement
HP Restricted © 2009 Hewlett-Packard Development Company, L.P. All rights reserved.